## Product Backlog
Product Name: | Exceptional Laptops and Supercomputers Always (ELSA) | [6 empty] | Complete Fields in Green!!!
Team ID: | 1
| Team Member Name | [5 empty] | Initials | Student ID
Required | Karun Dawadi | [5 empty] | KD | 1001660099
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 7 |  |  |  | Total | Total number of features (in column H)
1 | 3 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 3 | 0 |  |  | 2 | Total features left at the end of Sprint #2
3 | 3 | 0 |  |  | 3 | ...and so on
4 | 0 | 3
5 | -3 | 3
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 1 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly
OPT | 3 | 1 |  | 3 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product
DESKT | 4 | 1 |  | 1 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 5 | 1 |  | 1 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
GTK | 1 | 1 |  | 2 |  | Finished in Sprint 4 | Customer
OPTIONS | 1 | 1 |  | 1 | 1 | Finished in Sprint 4 | Inventory
RAM | 1 | 1 |  | 1 | 1 | Finished in Sprint 4 | Customer |  |  | R
Exceptional Laptops and Supercomputers Always (ELSA)

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2020-03-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-17
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 16 | 0
Day 2 Left | 15 | 1
Day 3 Left | 15 | 0
Day 4 Left | 15 | 0
Day 5 Left | 10 | 5
Day 6 Left | 6 | 4
Day 7 Left | 0 | 6
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Write the Customer class | Completed Day 5 | Test each class and method as it is written
2 | CUST |  | Write operator<< for Customer | Completed Day 5 | Commit and push AT LEAST once every class or update
3 | CUST |  | Write Store::add_customer, num_customers, and customer | Completed Day 5
4 | OPT |  | Write the Options class sans to_string | Completed Day 5
5 | OPT |  | Write Options::to_string and its operator<< | Completed Day 5
6 | OPT |  | Write Store::add_option (to Store), num_options, and option | Completed Day 6
7 | DESKT |  | Write the Desktop class with add_option method | Completed Day 6
8 | DESKT |  | Write the Desktop::price method | Completed Day 7 | Debug
9 | DESKT |  | Write operator<< for Desktop | Completed Day 7 | Debug
10 | DESKT |  | Write Store::new_desktop, add_option (to desktop), num_desktops, and desktop | Completed Day 7 | Debug
11 | ORDER |  | Write the Order associative class and constructor | Completed Day 2
12 | ORDER |  | Write Order::add_product | Completed Day 7 | Debug
13 | ORDER |  | Write Order::price | Completed Day 7 | Debug
14 | ORDER |  | Write Store::new_order, add_desktop, num_orders, and order | Completed Day 7 | Debug
15 | ORDER |  | Integrate and test with cse1325_prof/elsa/sprint_1/main.cpp | Completed Day 6
16 | ORDER |  | Ensure ALL CODE is on GitHub by deadline! | Completed Day 6
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2020-03-17 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-24
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 14
Day 1 Left | 14 | 0
Day 2 Left | 14 | 0
Day 3 Left | 14 | 0
Day 4 Left | 14 | 0
Day 5 Left | 14 | 0
Day 6 Left | 14 | 0
Day 7 Left | 0 | 14
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | GTK |  | Update mainwin.h | Completed Day 7 | Working
2 | GTK |  | Clean up mainwin.cpp | Completed Day 7 | Working
3 | GTK |  | Write Mainwin::Mainwin | Completed Day 7 | Working
4 | GTK |  | Implement the utility methods | Completed Day 7 | Working
5 | CUST |  | Implement utility methods | Completed Day 7 | Working
6 | OPT |  | Implement utility methods | Completed Day 7 | Working
7 | DESKT |  | Implement utility methods | Completed Day 7 | Need prof's help
8 | ORDER |  | Implement utility methods | Completed Day 7 | Need prof's help
9 | GTK |  | Implement entry methods | Completed Day 7 | Working
10 | GTK |  | Implement File exit and about | Completed Day 7 | Working
11 | OPT |  | Implement view methods | Completed Day 7 | Working
12 | CUST |  | Implement view methods | Completed Day 7 | Working
13 | DESKT |  | Implement view methods | Completed Day 7 | Working
14 | ORDER |  | Implement view methods | Completed Day 7 | Working
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2020-03-24 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-31
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2020-03-31 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-14
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 9
Day 1 Left | 9 | 0
Day 2 Left | 9 | 0
Day 3 Left | 9 | 0
Day 4 Left | 9 | 0
Day 5 Left | 9 | 0
Day 6 Left | 9 | 0
Day 7 Left | 0 | 9
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Get all of the program working till sprint 3 | Completed Day 7 | All code working till sprint 3.
2 | GTK |  | Add custom dialog | Completed Day 7 | This was the most fun and needed a lot of review.
3 | OPTIONS |  | Add derived options type | Completed Day 7
4 | RAM |  | Create Ram header | Completed Day 7
5 | RAM |  | Make Ram work | Completed Day 7
6 | GTK |  | Use grid to make custom dialog work | Completed Day 7
7 | RAM |  | Make Constructor | Completed Day 7
8 | RAM |  | Inherit methods | Completed Day 7
9 | RAM |  | Delegate to Options | Completed Day 7
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2020-04-14 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-21
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84